## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2025-03-24 | 42 | 2025-05-04 | 87
2 | 2025-05-05 | 0 | 2025-05-04 | 0
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2025-03-24 | 14 | 2025-04-06 | 31 | Planned |  | MVP | 1
2 | 2025-04-07 | 14 | 2025-04-20 | 45 | Planned |  | Design, Accounts, Filtering | 1
3 | 2025-04-21 | 14 | 2025-05-04 | 11 | Planned |  | Additional Features | 1
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 0
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
ST1 | As a landlord, I want a platform to list flats. | Ongoing | 5 | 1 |  | Website, MVP, Navigation, setup, includes flatmates putting up a listing
ST2 | As a student, I want to filter flats based on budget, amenities, etc. | Ongoing | 13 | 1 | High | Covers filtering by party/non-party, parking, furnished/unfurnished, power inclusion, etc.
ST3 | As a student, I want to see flats on a map. | Done | 13 | 1 | High | Google Maps API integration, custom map overlays
ST4 | As a landlord, I want to receive notifications when an application is submitted. | Planned | 21 | 2 | Medium | Setup notification system for landlords when applications are submitted.
ST5 | As a student, I want to track my applications. | Ongoing | 4 | 3 | Medium | Features application submission, tracking, landlord approvals, and rejections.
ST6 | As a student, I want updates on my applications. | Planned | 7 | 3 | High | Includes email/text notifications for application updates, new listings, etc.
ST7 | As a Dunedin landlord, I want to see how many people have viewed my listing, so that I can gauge interest in my property. | Planned | 6 | 2 | High | Can be used for analytics of multiple listings later
ST8 | As a Dunedin student looking for a flatmate, I want to verify that an applicant is a real person by requiring profile photos and student ID verification, so that I can avoid scams and unreliable tenants. | Planned | 6 | 2 | Low
ST9 | As a Dunedin student looking for a flat, I want to compare multiple flats side by side, so that I can evaluate my options more easily. | Planned | 6 | 2 | Low | Favourites
ST10 | As a property manager, I want analytics on listing performance, so that I can optimize my advertising strategy. | Planned | 6 | 2 | Low
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 137 |  | Sprint count | 5
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 25 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 25 |  | Trend count | 7 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 25 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 25 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 25 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 3
Original estimate - Avg |  |  | 5
Original estimate - Max |  |  | 8 |  | Standard Dev. | 2.8284
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 28
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 6
Realized + St. Dev |  |  | 6
Realized - St. Dev |  |  | 6
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 137 | 23 | 23 | 137 | 137 | 137 | 0 | 0 | 137 | 137.6667 | 137.6667 | 0 | 25 | 25 | 25
2 | 114 | 29 | 27 | 137 | 114 | 114 | 0 | 0 | 114 | 112.6667 | 112.6667 | 0 | 25 | 25 | 25
3 | 87 | 31 |  | 137 | 87 | 87 | 0 | 0 | 87 | 87.6667 | 87.6667 | 0 | 25 | 25 | 25
4 | 56 | 28 |  | 137 | 0 | 0 | 56 | 56 | 56 | 62.6667 | 62.6667 | 0 | 25 | 25 | 25
5 | 28 | 28 |  | 137 | 0 | 0 | 28 | 28 | 28 | 37.6667 | 37.6667 | 0 | 25 | 25 | 25
6 | [9 empty] | 12.6667 | 12.6667 | 0 | 25 | 25 | 25
7 | [9 empty] | 0 | 0 | 0 | 25 | 25 | 25
8 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
9 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
10 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
11 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
12 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
13 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
14 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
15 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
16 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
17 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
18 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
19 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
20 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
21 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
22 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
23 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
24 | [9 empty] | 0 |  | 0 | 25 | 25 | 25
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 14 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 264 | 244 | 224 | 196 | 176 | 160 | 113 | 84 | 67 | 56 | 49 | 38 | 33 | 21
Task rows | 27 | Done days | 13 |  | 264 | 245.1429 | 226.2857 | 207.4286 | 188.5714 | 169.7143 | 150.8571 | 132 | 113.1429 | 94.2857 | 75.4286 | 56.5714 | 37.7143 | 18.8571
Warning! These are necessary |  | Trend |  |  | 125.4 | 116.8 | 108.2 | 99.6 | 91 | 82.4 | 73.8 | 65.2 | 56.6 | 48 | 39.4 | 30.8 | 22.2 | 13.6 | 5
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7; 8: 8; 9: 9; 10: 10; 11: 11; 12: 12; 13: 13; 14: 14
Setup Repo / Website | 1 | JC | Done | 5 | 1: 0
Database | 1 | Finn | Done | 21 | 1: 18; 2: 15; 3: 15; 4: 15; 5: 15; 6: 5; 7: 0
addFlat | 1 | Finn | Done | 13 | 1: 13; 2: 12; 3: 11; 4: 10; 5: 9; 6: 4; 7: 4; 8: 0
Applications | 5 | Finn | Done | 13 | 1: 13; 2: 13; 3: 12; 4: 11; 5: 10
Sessions | 5 | Finn | Done | 21 | 1: 21; 2: 21; 3: 21; 4: 21; 5: 21; 6: 21; 7: 16; 8: 11; 9: 0
getFlats | 1 | Finn | Done | 5 | 1: 5; 2: 5; 3: 5; 4: 0
Page view of a single Flat | 1 | Finn | Done | 5 | 1: 5; 2: 5; 3: 5; 4: 5; 5: 5; 6: 5; 7: 5
POIs | 3 | JC | Done | 5 | 1: 5; 2: 5; 3: 5; 4: 5; 5: 5
Basic Filtering | 2 | JC | Done | 13 | 1: 13; 2: 13; 3: 13; 4: 9; 5: 9; 6: 7; 7: 4; 8: 4; 9: 4; 10: 4; 11: 4; 12: 0
editFlat | 1 | JC | Done | 8 | 1: 8; 2: 8; 3: 8; 4: 8; 5: 8; 6: 8; 7: 8; 8: 8; 9: 8; 10: 8
deleteFlat | 1 | JC | Done | 5 | 1: 5; 2: 5; 3: 5; 4: 5; 5: 5; 6: 5
Unit Testing | 1 | JC | Done | 13 | 1: 13; 2: 13; 3: 13; 4: 10; 5: 6; 6: 0
CI / Integration | 1 | JC | Done | 5 | 1: 4; 2: 4; 3: 1
Tags | 2 | JC | Done | 8 | 1: 8; 2: 8; 3: 0
Distance calculations | 3 | JC | Done | 8 | 1: 8; 2: 5; 3: 0
Map Filter [with Tags] | 2 | JC | Done | 13 | 1: 13; 2: 13; 3: 11; 4: 8; 5: 0
Testing | 1 | JC | Done | 13 | 1: 13; 2: 13; 3: 13; 4: 13; 5: 13; 6: 13; 7: 3; 8: 0
Basic Map View | 3 | Ben | Done | 8 | 1: 2; 2: 0
Basic Markers W Photos | 3 | Ben | Done | 5 | 1: 5; 2: 5; 3: 2; 4: 0
Deployment Debugging | 1 | Ben | Done | 7 | 1: 7; 2: 7; 3: 7; 4: 7; 5: 7; 6: 0
Adding Custom Markers | 3 | Ben | Done | 9 | 1: 9; 2: 9; 3: 9; 4: 9; 5: 9; 6: 9; 7: 9; 8: 9; 9: 9; 10: 2; 11: 0
Map Debugging | 3 | Ben | Done | 5 | 1: 5; 2: 5; 3: 5; 4: 5; 5: 5; 6: 5; 7: 5; 8: 5; 9: 5; 10: 5; 11: 5; 12: 5; 13: 5; 14: 0
Scroll Through Photos | 9 | Ben | Done | 12 | 1: 12; 2: 12; 3: 12; 4: 12; 5: 12; 6: 12; 7: 12; 8: 12; 9: 12; 10: 12; 11: 12; 12: 12; 13: 6; 14: 0
Redesign & Model Individual Flat page | 1 | Ben | Done | 18 | 1: 18; 2: 18; 3: 18; 4: 18; 5: 18; 6: 18; 7: 18; 8: 18; 9: 18; 10: 18; 11: 17; 12: 16; 13: 10; 14: 0
CSS Styling | 1 | Amelia | Ongoing | 8 | 1: 8; 2: 5
Website Design | 1 | Amelia | Ongoing | 13 | 1: 8; 2: 5; 3: 5; 4: 5; 5: 3; 6: 1
Landing Page | 1 | Amelia | Done | 5 | 1: 5; 2: 0
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
Sprint implementation days | 14 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 56 | 54 | 49 | 38 | 25 | 23 | 16 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Task rows | 16 | Done days | 14 |  | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Warning! These are necessary |  | Trend |  |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6; 7: 7; 8: 8; 9: 9; 10: 10; 11: 11; 12: 12; 13: 13; 14: 14
Search with Tags |  | JC | Done | 13 | 1: 13; 2: 12; 3: 1; 4: 0
Caching |  | Finn | Done | 3 | 1: 3; 2: 2; 3: 0
Only the owner can edit listing |  | Finn | Done | 3 | 1: 3; 2: 3; 3: 3; 4: 3; 5: 3; 6: 0
Filter by distance to Uni on Map |  | Ben | Done | 5 | 1: 3; 2: 0; 3: 2
Analytics |  |  | Planned
Dashboard |  | Finn | Done
Push Notifications via Email |  | JC | Ongoing | 21 | 1: 21; 2: 21; 3: 21; 4: 13; 5: 13; 6: 13; 7: 13; 8: 13; 9: 13; 10: 13; 11: 13; 12: 13; 13: 13; 14: 13
Verification |  |  | Planned
Applicant Comparison |  | Finn | Done
Flat Comparison |  |  | Planned
Flat Favourites |  |  | Planned
Landlord Account |  |  | Done | 3 | 1: 3; 2: 3; 3: 3; 4: 3; 5: 3; 6: 0
Semester Durations |  |  | Planned
Reject and Acknowledging users for flats |  | Finn | Done | 5 | 1: 5; 2: 5; 3: 5; 4: 3; 5: 1; 6: 0
Add Link To Google Maps |  | Ben | Done | 3 | 1: 3; 2: 3; 3: 3; 4: 3; 5: 3; 6: 3; 7: 0
Global Styles |  | Amelia | Done | 13 | 1: 7; 2: 3; 3: 2; 4: 1; 5: 0
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
Sprint implementation days | 14 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 46 | 35 | 27 | 22 | 18 | 17 | 15 | 4 | [16 empty] | #REF! | #REF!
Task rows | 8 | Done days | 7 |  | 46 | 42.7143 | 39.4286 | 36.1429 | 32.8571 | 29.5714 | 26.2857 | 23 | 19.7143 | 16.4286 | 13.1429 | 9.8571 | 6.5714 | 3.2857
Warning! These are necessary |  | Trend |  |  | 30.8 | 26.9 | 23 | 19.1 | 15.2 | 11.3 | 7.4 | 3.5
template rows |  | Trend Days | 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 30.8 1: 1; 26.9 2: 2; 23 3: 3; 19.1 4: 4; 15.2 5: 5; 11.3 6: 6; 7.4 7: 7; 3.5 8: 8; 3.5 9: 9; 3.5 10: 10; 3.5 11: 11; 3.5 12: 12; 3.5 13: 13; 3.5 14: 14
Responsive Design for Mobile |  | Amelia | Done | 13 | 30.8 1: 6; 26.9 2: 4; 23 3: 2; 19.1 4: 2; 15.2 5: 2; 11.3 6: 1; 7.4 7: 0
Add In Search for Closest Flat |  | Ben | Done | 10 | 30.8 1: 6; 26.9 2: 3; 23 3: 3; 19.1 4: 3; 15.2 5: 3; 11.3 6: 3; 7.4 7: 1; 3.5 8: 0; 3.5 24: #REF!; 3.5 25: #REF!
|  | Ben | Planned | 3 | 30.8 1: 3; 26.9 2: 3; 23 3: 3; 19.1 4: 3; 15.2 5: 3; 11.3 6: 3; 7.4 7: 0; 3.5 24: #REF!; 3.5 25: #REF!
Application Acknowledge/Reject |  | Finn | Done | 7 | 30.8 1: 7; 26.9 2: 5; 23 3: 3; 19.1 4: 0
Push Notifications via Email |  | JC | Done | 13 | 30.8 1: 13; 26.9 2: 12; 23 3: 11; 19.1 4: 10; 15.2 5: 9; 11.3 6: 8; 7.4 7: 3; 3.5 8: 0
Verification |  |  | Planned
Flat Favourites |  | Ben | Done | 5 | 30.8 1: 5; 26.9 2: 5; 23 3: 5; 19.1 4: 3; 15.2 5: 2; 11.3 6: 1; 7.4 7: 0
Final Presentation |  | All | Done | 21 | 30.8 1: 21; 26.9 2: 13; 23 3: 13; 19.1 4: 13; 15.2 5: 7; 11.3 6: 5; 7.4 7: 4; 3.5 8: 4; 3.5 9: 4; 3.5 10: 4; 3.5 11: 4; 3.5 12: 3; 3.5 13: 3; 3.5 14: 0
Semester Durations |  |  | Planned
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task
Responsible Person: JC
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: Finn
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: Finn
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person: Finn
Initial Estimate | 9 | Work Done |  | Work Left